## DCM971
SLP01 Project Schedule
Task List | Due time | Status
Kick off meeting | 2019-05-14 | open
MD
3D file design | 2019-05-30 | open
2D file for layout release | 2019-05-14 | CLOSE
3D design review | 2019-06-02 | open
Plastic tooling | 2019-06-03 | open
T0 plastic samples | 2019-06-28 | open
HW
SCH | 2019-05-22 | open
SCH review | 2019-05-23 | open
PCB Layout | 2019-05-30 | open
PCB Layout review | 2019-05-31 | open
Release Gerber | 2019-05-31 | open
SW
BLE software developing | 2019-06-20 | open
BG96 Modem software developing (Need Sam to help to do the Application) | 2019-06-20 | open
Assembly
SMT（100PCS） | 2019-06-20 | open
Samples Test | 2019-06-25 | open
Antenna Tuning | 2019-06-30 | open
Engineer Samples without final Antenna delivery（10PCS） | 2019-06-30 | open
T1 Plastic with Antenna Samples delivery（10PCS） | 2019-07-15 | open